## Plan
ID | Task | Duration_wd | Depends | Owner | Start | Finish
A | Requirements | 3 | none | Product | 2026-09-01 | 2026-09-03
B | Solution design | 4 | A | Engineering | 2026-09-04 | 2026-09-09
C | Legal review | 5 | A | Legal | 2026-09-04 | 2026-09-10
D | Build | 8 | B | Engineering | 2026-09-10 | 2026-09-21
E | Content | 6 | B | Marketing | 2026-09-10 | 2026-09-17
F | UAT | 4 | D,E | Product | 2026-09-22 | 2026-09-25
G | Training | 3 | C,F | Enablement | 2026-09-28 | 2026-09-30
H | Launch | 1 | G | Program Lead | 2026-10-01 | 2026-10-01
Rule: successor starts next working day after ALL predecessors finish. Weekends off. No public holidays.
Critical path: A-B-D-F-G-H = 3+4+8+4+3+1 = 23 working days. Launch 2026-10-01 HIT.
Start_check_weekday_Sep1
Launch_is_Oct1

## Gantt
ID | Task | 2026-09-01 | 09-02 | 09-03 | 09-04 | 09-07 | 09-08 | 09-09 | 09-10 | 09-11 | 09-14 | 09-15 | 09-16 | 09-17 | 09-18 | 09-21 | 09-22 | 09-23 | 09-24 | 09-25 | 09-28 | 09-29 | 09-30 | 10-01
A | Requirements | █ | bar: 09-02 to 09-03
B | Solution design | bar: 09-04 to 09-09
C | Legal review | bar: 09-04 to 09-10
D | Build | bar: 09-10 to 09-21
E | Content | bar: 09-10 to 09-17
F | UAT | bar: 09-22 to 09-25
G | Training | bar: 09-28 to 09-30
H | Launch | bar: 10-01

## RACI
Task | Product | Eng | Legal | Mkt | Enablement | Program Lead | COO | InfoSec
A Requirements | A/R | C | I | I | I | I | I | I
B Design | C | A/R | I | C | I | I | I | C
C Legal | I | I | A/R | I | I | I | C | I
D Build | C | A/R | I | I | I | I | I | C
E Content | C | I | C | A/R | I | I | I | I
F UAT | A/R | R | I | C | C | C | I | C
G Training | C | I | I | C | A/R | I | I | I
H Launch | C | C | C | C | C | A/R | C | I
Exactly one Accountable (A) per task. InfoSec Consulted during UAT. Sponsor=COO. Marketing 14-15 Sep covered by deputy; A stays with Marketing.

## Risk_Register
ID | Risk | Impact | Mitigation
R1 | Legal delay 3 days | C ends 15 Sep, still before F ends 25 Sep; not on critical path unless delay exceeds F | Check C on 10 Sep
R2 | Only one UAT environment | F cannot split; 4 days no backup env | Exclusive calendar before 21 Sep
R3 | Marketing 14-15 Sep leave | E in progress those days | Deputy covers; sign-off before 13 Sep
R4 | Zero buffer to 1 Oct | Any +1 working day misses launch | Daily standup on D/F; freeze scope at end of B
R5 | Public holidays ignored per brief | — | Per task assumption