## Schedule
项目计划（工作日排程；起始 2026-09-01；后置任务从所有前置完成后的下一个工作日开始；WORKDAY/NETWORKDAYS 公式）
项目开始日 | 2026-09-01 |  | 目标上线日 | 2026-10-01
ID | Task | Duration (days) | Depends on | Owner | Early Start | Early Finish | Late Start | Late Finish | Total Float (days) | Critical?
A | Requirements | 3 | none | Product
B | Solution design | 4 | A | Engineering
C | Legal review | 5 | A | Legal
D | Build | 8 | B | Engineering
E | Content | 6 | B | Marketing
F | UAT | 4 | D,E | Product
G | Training | 3 | C,F | Enablement
H | Launch | 1 | G | Program Lead
计划上线日（H 的 Early Finish）
是否满足 2026-10-01 目标
关键路径
关键路径总工期（工作日）
Legal 延迟 3 天是否影响上线（C 浮动 ≥3？）
Early Start = 前置任务 Early Finish 的下一个工作日；Early Finish = WORKDAY(ES, Duration−1)；Late Finish 由后继任务 Late Start 倒推；Total Float = NETWORKDAYS(ES, LS) − 1；Float=0 为关键路径。
Formulas:
Early Finish = WORKDAY([Early Start],[Duration (days)]-1)
Late Start = WORKDAY([Late Finish],-([Duration (days)]-1))
Late Finish = WORKDAY(MIN([Late Start, row below],H6),-1)
Late Finish = WORKDAY([Late Start, row below],-1)
Total Float (days) = NETWORKDAYS([Early Start],[Late Start])-1
Early Start = WORKDAY([Early Finish, row above],1)
Early Start = WORKDAY(MAX(G7,[Early Finish, row above]),1)

## Gantt
简易甘特图（■ = 工作日内执行；灰 = 周末；公式驱动，随 Schedule 变化）
ID | Task | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05 | 2026-09-06 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03
红=关键路径任务，蓝=非关键任务，灰=周末。上线日 2026-10-01（周四）。

## RACI
RACI 矩阵（每项只有一个 A）
ID | Task | Sponsor (COO) | Program Lead | Product | Engineering | Legal | Marketing | Enablement | InfoSec | A 计数（应=1）
A | Requirements | I | C | A/R | C | C | I | I | I
B | Solution design | I | C | C | A/R | I | I | I | C
C | Legal review | I | C | C | I | A/R | I | I | I
D | Build | I | C | C | A/R | I | I | I | C
E | Content | I | C | C | I | C | A/R | I | I
F | UAT | I | C | A/R | R | I | R | I | C
G | Training | I | C | C | I | C | C | A/R | I
H | Launch | I | A/R | R | R | C | R | R | C
R=负责执行 A=最终负责（唯一） C=被咨询 I=被告知。InfoSec 在 UAT（F）期间为 C，符合题内要求；Sponsor 全程 I，H 上线由 Program Lead 负责。

## Risk Register
风险登记册
# | 风险 | 影响任务 | 可能性 | 影响 | 等级 | 分析（基于排程） | 应对 | 负责人 | 触发/监控
1 | Legal review 可能延迟 3 天 | C→G | 中 | 低 | 低 | C 的总浮动为 11 个工作日（9/10 完成，G 9/28 开始），延迟 3 天不影响上线 | 接受；每周跟踪 C 进度，若延迟超过 8 天升级 | Legal / Program Lead | C 未在 9/15 前完成即预警
2 | UAT 环境只有一个 | F | 中 | 高 | 高 | F 在关键路径且无浮动；环境故障或被占用直接推迟上线 | UAT 前一周冻结环境；准备数据回滚脚本；申请备用环境预算 | Engineering / Product | UAT 前 9/18 环境就绪检查
3 | Marketing 负责人 9/14–15 休假 | E | 高（已知） | 低 | 低 | E 9/10–9/17 执行，休假 2 天在其中；E 总浮动 2 个工作日，由副手覆盖则不影响 | 副手在 9/11 前完成交接；若 E 延迟 >2 天将进入关键路径 | Marketing | E 9/15 中期检查
4 | 关键路径零浮动（A-B-D-F-G-H） | 全部关键任务 | 中 | 高 | 高 | 计划上线日恰为 10/1，任何关键任务延迟 1 天即错过目标 | Build（D，8 天）每日站会；提前定义 UAT 通过标准；准备 10/2 应急沟通 | Program Lead | 任一关键任务 EF 晚于计划即升级 Sponsor
5 | Build 与 Content 同时依赖 Design 输出 | D、E | 中 | 中 | 中 | B 若延迟同时推迟 D 与 E | B 完成标准前置确认；D 可在 B 9/9 前分批接收设计 | Engineering | B 9/9 完成确认
6 | InfoSec 在 UAT 期间未及时参与 | F | 中 | 中 | 中 | InfoSec 为 C；反馈延迟会拖长 F | 9/15 前发出 UAT 计划并预约 InfoSec 评审时段 | Product | 9/15 邀请确认