## Schedule
ID | Task | Duration(d) | Depends on | Owner | Start | Finish
A | Requirements | 3 | none | Product | 2026-09-01 | 2026-09-03
B | Solution design | 4 | A | Engineering | 2026-09-04 | 2026-09-09
C | Legal review | 5 | A | Legal | 2026-09-04 | 2026-09-10
D | Build | 8 | B | Engineering | 2026-09-10 | 2026-09-21
E | Content | 6 | B | Marketing | 2026-09-10 | 2026-09-17
F | UAT | 4 | D,E | Product | 2026-09-22 | 2026-09-25
G | Training | 3 | C,F | Enablement | 2026-09-28 | 2026-09-30
H | Launch | 1 | G | Program Lead | 2026-10-01 | 2026-10-01

## Gantt
ID | Task | Start Offset(workdays) | Duration | Critical Path?
A | Requirements | 0 | 3 | Yes
B | Solution design | 3 | 4 | Yes
C | Legal review | 3 | 5 | No
D | Build | 7 | 8 | Yes
E | Content | 7 | 6 | No
F | UAT | 16 | 4 | Yes
G | Training | 19 | 3 | Yes
H | Launch | 22 | 1 | Yes

## RACI
Task | A (Accountable) | R (Responsible) | C (Consulted) | I (Informed)
A Requirements | Product | Product | Program Lead | COO (Sponsor)
B Solution design | Engineering | Engineering | Product | Program Lead
C Legal review | Legal | Legal | Product | Program Lead
D Build | Engineering | Engineering | Product | Program Lead
E Content | Marketing | Marketing | Engineering | Program Lead
F UAT | Product | Product/Engineering | InfoSec | Program Lead
G Training | Enablement | Enablement | Product | Program Lead
H Launch | Program Lead | Program Lead | All | COO (Sponsor)

## Risks
Risk | Impact | Mitigation
Legal 可能延迟 3 天 | C 完成由 9/10 推迟到约 9/15，但不影响关键路径（G 需 9/28 前） | 提前介入、预留缓冲
UAT 环境只有一个 | UAT 可能排队/冲突 | 提前预约环境、错峰
Marketing 负责人 9/14-15 休假 | E（Content）可能延迟 | 副手覆盖（题内已注明）